## Sheet1
Fase | Onderdeel | week 0 | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | Legenda
Concept | concept bedenken | [12 empty] | Alice | bar: week 0
| eisen opstellen | [12 empty] | Ben | bar: week 0 to week 1
| rolverdeling maken | [12 empty] | Corne | bar: week 0
| Github opzetten | [12 empty] | Dave | bar: week 0
| Benodigdheden onderzoeken | [12 empty] | Elise | bar: week 1 to week 2
| Concept presenteren | [12 empty] | Fransje | bar: week 1 to week 2
Ontwerp | Schetsen maken | [12 empty] | Iedereen | bar: week 2 to week 3
database ontwerp | bar: week 2 to week 3
componenten overzicht maken | bar: week 2 to week 3
Pitch houden GONOGO | bar: week 3 to week 4
Uitvoering | Frontend | bar: week 4 to week 5
Database | bar: week 4 to week 5
Communicatie | bar: week 4 to week 5
Interactie 1 | bar: week 5 to week 6
Interactie 2 | bar: week 5 to week 6
Interactie 3 | bar: week 5 to week 6
testen | Samenvoeging test | bar: week 6 to week 7
UI test | bar: week 6 to week 8
data weergave testen | bar: week 6 to week 8
Interacties testen | bar: week 6 to week 8
Clean test | bar: week 8 to week 9
testplan en resultaten beschrijven | bar: week 9
Oplevering | Documentatie opleveren | bar: week 9 to week 10
Code opleveren | bar: week 9 to week 10
Eind presentatie | bar: week 10